## OPPM
Project Leader: vai | [8 empty] | Project Name: National Health Record Sharing System (NHRS)
Project Objective: | [5 empty] | Build Cambodia's national FHIR-compliant health record sharing platform with AI-powered clinical assistance, serving 500+ health facilities
Deliverable Output: | [5 empty] | FHIR R4 compliant API gateway with 99.9% uptime SLA, Patient consent management portal (web + mobile responsive), Clinician mobile app (iOS/Android) for bedside record access, AI-powered clinical decision support module, National health data warehouse with analytics dashboard, Integration adapters for 5 existing hospital information systems, Operations runbook and MoH IT team training materials
Start Date: | [5 empty] | 3/18/26
Deadline: | [5 empty] | 5/1/26
Sub Objective | [5 empty] | Major Tasks (Deadline) |  |  | Project Completed By: 5/1/26 | [7 empty] | Owner / Priority
1. Requirements & Regulatory Compliance
✓ |  |  | ✓ |  |  | 1.1 Stakeholder requirements gathering (3/25/26) |  |  | ● | ● | [6 empty] | A | B
✓ | ✓ |  |  |  |  | 1.2 MoH policy review & gap analysis (3/20/26) |  |  | ● | [7 empty] | A
✓ |  | ✓ |  |  |  | 1.3 FHIR R4 resource mapping workshop (3/24/26) |  |  |  | ● | [7 empty] | A
| ✓ |  |  |  |  | 1.4 Data privacy impact assessment (3/25/26) |  |  |  | ● | [6 empty] | A
✓ | ✓ |  |  |  |  | 1.5 Regulatory framework documentation (3/28/26) |  |  |  | ● | [6 empty] | B | A
✓ |  | ✓ |  |  |  | 1.6 HL7 FHIR conformance statement (3/27/26) |  |  |  | ● | [7 empty] | A
| ✓ |  | ✓ |  |  | 1.7 Consent management policy design (3/28/26) |  |  |  | ● | [6 empty] | A
| ✓ |  |  |  |  | 1.8 Security classification matrix (3/28/26) |  |  |  | ● | [7 empty] | A
2. System Architecture & Infrastructure
| ✓ |  |  | ✓ |  | 2.1 Cloud infrastructure provisioning (4/1/26) |  |  |  | ● | ● | [5 empty] | A
|  |  |  | ✓ |  | 2.2 Kubernetes cluster setup (3/28/26) |  |  |  | ● | [6 empty] | A
|  |  |  | ✓ |  | 2.3 Database cluster (PostgreSQL HA) (3/31/26) |  |  |  |  | ● | [6 empty] | A
|  |  |  | ✓ |  | 2.4 CI/CD pipeline configuration (4/1/26) |  |  |  |  | ● | [5 empty] | A
✓ |  | ✓ |  | ✓ |  | 2.5 FHIR API gateway design (4/4/26) |  |  |  |  | ● | ● |  |  |  |  | B | A
✓ |  | ✓ |  |  |  | 2.6 HAPI FHIR server deployment (4/1/26) |  |  |  |  | ● | [6 empty] | A
✓ | ✓ |  |  |  |  | 2.7 OAuth2/SMART on FHIR auth (4/4/26) | [5 empty] | ● |  |  |  |  | A
| ✓ |  |  | ✓ |  | 2.8 API rate limiting & throttling (4/4/26) | [5 empty] | ● | [5 empty] | B
3. Core Platform Development
✓ |  | ✓ | ✓ |  |  | 3.1 Patient record management module (4/10/26) | [5 empty] | ● |  |  |  |  | A
✓ |  | ✓ |  |  |  | 3.2 Patient FHIR resource API (4/4/26) | [5 empty] | ● |  |  |  |  | A
✓ |  |  | ✓ |  |  | 3.3 Clinical document storage (4/7/26) | [5 empty] | ● | [5 empty] | A
| ✓ |  | ✓ |  |  | 3.4 Patient consent engine (4/10/26) | [5 empty] | ● |  |  |  |  | A
✓ |  | ✓ |  |  |  | 3.5 Encounter & observation tracking (4/11/26) | [5 empty] | ● |  |  |  |  | C | A
✓ |  | ✓ |  |  |  | 3.6 Encounter workflow engine (4/7/26) | [5 empty] | ● | [5 empty] | A
✓ |  | ✓ |  |  |  | 3.7 Vital signs & observations API (4/9/26) | [5 empty] | ○ |  |  |  |  | A
✓ |  | ✓ |  |  | ✓ | 3.8 Lab results integration (4/11/26) | [6 empty] | ○ |  |  |  |  | A
✓ |  |  | ✓ |  | ✓ | 3.9 Medication & prescription management (4/14/26) | [5 empty] | ○ | ○ |  |  |  | A
✓ | [5 empty] | 3.10 MedicationRequest API (4/10/26) | [5 empty] | ○ |  |  |  |  | A
[5 empty] | ✓ | 3.11 Drug interaction checker (AI) (4/13/26) | [6 empty] | ○ |  |  |  |  | A
✓ |  |  | ✓ |  |  | 3.12 Pharmacy dispensation tracking (4/14/26) | [6 empty] | ○ |  |  |  | B
4. Interoperability & Data Exchange
✓ |  | ✓ |  | ✓ |  | 4.1 Multi-facility data exchange (4/18/26) | [6 empty] | ○ | ○ |  |  | B | A
✓ |  | ✓ |  |  |  | 4.2 FHIR Subscription framework (4/13/26) | [6 empty] | ○ |  |  |  |  | A
|  | ✓ |  | ✓ |  | 4.3 Master Patient Index (MPI) (4/16/26) | [6 empty] | ○ | ○ |  |  | A
|  | ✓ |  |  |  | 4.4 Data transformation pipelines (4/18/26) | [7 empty] | ○ |  |  |  | A
5. AI & Clinical Decision Support
|  |  | ✓ |  | ✓ | 5.1 AI diagnostic assistant (4/22/26) | [6 empty] | ○ | ○ |  |  | A
[5 empty] | ✓ | 5.2 Clinical NLP engine (4/17/26) | [6 empty] | ○ |  |  |  | A
[5 empty] | ✓ | 5.3 Differential diagnosis engine (4/20/26) | [7 empty] | ○ |  |  |  | A
|  |  | ✓ |  | ✓ | 5.4 Treatment recommendation API (4/22/26) | [7 empty] | ○ |  |  | A
6. Security, Testing & Deployment
| ✓ |  |  |  |  | 6.1 Security hardening & penetration testing (4/24/26) | [7 empty] | ○ |  |  | B | A
| ✓ |  |  |  |  | 6.2 AES-256-GCM encryption layer (4/20/26) | [7 empty] | ○ |  |  |  | A
| ✓ |  |  |  |  | 6.3 OWASP security assessment (4/22/26) | [7 empty] | ○ |  |  | A
| ✓ |  |  |  |  | 6.4 Penetration test (external) (4/24/26) | [7 empty] | ○ |  |  |  | A
|  | ✓ | ✓ | ✓ |  | 6.5 Integration testing & UAT (4/28/26) | [7 empty] | ○ | ○ |  | A
|  | ✓ |  | ✓ |  | 6.6 Cross-facility integration test (4/25/26) | [7 empty] | ○ |  |  | A
|  |  |  | ✓ |  | 6.7 Load testing (500 concurrent users) (4/26/26) | [8 empty] | ○ |  |  | A
|  |  | ✓ |  |  | 6.8 UAT with clinical staff (4/28/26) | [8 empty] | ○ |  | A
| ✓ |  |  | ✓ |  | 6.9 Production deployment & go-live (5/1/26) | [8 empty] | ○ |  | A | A
|  |  |  | ✓ |  | 6.10 Blue-green deployment setup (4/28/26) | [8 empty] | ○ |  | A
|  |  |  | ✓ |  | 6.11 Production monitoring & alerting (4/30/26) | [8 empty] | ○ |  |  | A
| ✓ |  |  | ✓ |  | 6.12 Go-live support & handover (5/1/26) | [8 empty] | ○ |  | A
# People working on the project
1 | 2 | 3 | 4 | 5 | 6 |  |  |  | 3/16 | 3/23 | 3/30 | 4/6 | 4/13 | 4/20 | 4/27 | 5/4 | vai | cheongchoonv
Sub Obj 1 | Sub Obj 2 | Sub Obj 3 | Sub Obj 4 | Sub Obj 5 | Sub Obj 6
[6 empty] | Major Tasks |  | Target Dates
Summary & Forecast
[6 empty] | Sub Objectives |  | Costs
Summary Deliverable
1. FHIR R4 compliant API gateway with 99.9% uptime SLA
2. Patient consent management portal (web + mobile responsive)
3. Clinician mobile app (iOS/Android) for bedside record access
4. AI-powered clinical decision support module
5. National health data warehouse with analytics dashboard
6. Integration adapters for 5 existing hospital information systems
7. Operations runbook and MoH IT team training materials
Forecast
1. Core platform MVP deployed to 3 pilot hospitals by May 1, 2026
2. Full national rollout to 500+ facilities by Q3 2026
3. 1M patient records migrated within first 6 months
4. AI diagnostic accuracy target: 85%+ concordance with specialist diagnoses
5. System handles 500 concurrent users with <200ms API response time
Risk
[AMBER] Legacy hospital systems may not support HL7v2-to-FHIR conversion
[RED] Patient data privacy breach during cross-facility exchange
[AMBER] Clinical staff resistance to new digital workflows
[AMBER] AI diagnostic model bias on underrepresented conditions
[RED] Internet connectivity issues at rural health facilities
[GREEN] Regulatory changes requiring architecture modifications
Legend: | ○ Planned | ● In Progress | ● Completed | ● At Risk | ● Blocked
Owners: | A = Primary | B = Secondary | C = Support